MERIDIAN CIVIL WORKS LLC

Northgate Bridge Retrofit - Monthly Status Report

Reporting period: June 2026  |  Report date: July 2, 2026  |  Report no. 14

Project summary

Project number NB-2107 remains on schedule for substantial completion in November 2026. Overall completion stands at 68 percent against a planned 66 percent. Spend to date is $8,412,000 of the approved $12,600,000 budget. Project manager is Dana Whitcombe; the client representative is R. Okonjo of the Halvern County Department of Transportation. Overall status this period is YELLOW, driven by the steel delivery risk described in the risk register.

Milestone schedule

| Milestone | Baseline date | Forecast date | Status | % Complete |
| --- | --- | --- | --- | --- |
| Design freeze and permits | 2025-09-12 | 2025-09-12 | Complete | 100% |
| Pier foundation strengthening | 2026-01-30 | 2026-01-27 | Complete | 100% |
| Deck section removal (north span) | 2026-03-20 | 2026-03-24 | Complete | 100% |
| Structural steel delivery | 2026-06-15 | 2026-07-08 | Delayed | 80% |
| Steel erection and welding | 2026-08-01 | 2026-08-12 | Not started | 0% |
| Deck pour and curing | 2026-09-15 | 2026-09-22 | Not started | 0% |
| Load testing and inspection | 2026-10-20 | 2026-10-27 | Not started | 0% |
| Substantial completion | 2026-11-15 | 2026-11-20 | Forecast | - |

Progress this period

North span deck removal finished four days behind baseline after a two-day weather hold. Pier 3 bearing replacement passed county inspection on June 18. Night-shift lane closures ran without incident; the public-comment line logged six calls, all resolved. Fabrication of girder sections G-11 through G-18 is complete at the Ridgeline Steel yard and awaiting transport permits.

Procurement issued purchase order PO-2107-44 for expansion joints ($214,500) and confirmed the elastomeric bearing order remains within budget. Two requests for information were answered by the design engineer with no schedule impact.

Risk register

| ID | Risk description | Probability | Impact | Owner | Mitigation | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-03 | Structural steel delivery slips past July 8 | High | High | D. Whitcombe | Transport permits escalated to state DOT; partial delivery accepted June 30 | Open |
| R-07 | Concrete supplier capacity during September pour | Medium | High | L. Ferraro | Second supplier under standby agreement signed May 2026 | Open |
| R-09 | Peregrine falcon nesting near pier 5 restarts seasonal work window | Low | Medium | S. Anand | Environmental monitor on call; work sequenced away from pier 5 until August | Monitoring |
| R-11 | Night-closure noise complaints trigger permit review | Low | Low | M. Beaudry | Sound blankets installed on generators; complaint log shared with county weekly | Closed |
| R-12 | Weld inspection backlog at county lab | Medium | Medium | L. Ferraro | Third-party certified inspector approved as backup on June 22 | Open |
| R-14 | Lane-closure permit renewal lapses over the county holiday recess | Medium | Medium | M. Beaudry | Renewal filed 60 days early; standing agenda item with county permits office | Open |
| R-15 | Unmapped utility duct bank near pier 2 approach | Low | High | S. Anand | Ground-penetrating radar survey scheduled for July 14 before excavation | Open |
| R-16 | Barge crane availability clashes with harbor dredging schedule | Medium | High | D. Whitcombe | Reservation confirmed in writing with operator; dredging liaison meeting monthly | Monitoring |
| R-17 | Certified welder shortage during August erection peak | Medium | Medium | L. Ferraro | Two additional crews pre-qualified through the regional trades council | Open |

Budget position

| Cost category | Approved budget | Committed | Spent to date | Variance |
| --- | --- | --- | --- | --- |
| Structural steel and fabrication | $4,150,000 | $4,208,000 | $3,366,400 | ($58,000) |
| Civil and foundation works | $3,900,000 | $3,845,000 | $3,076,000 | $55,000 |
| Traffic control and safety | $980,000 | $965,000 | $723,750 | $15,000 |
| Engineering and inspection | $1,470,000 | $1,470,000 | $882,000 | $0 |
| Contingency | $2,100,000 | $364,000 | $363,850 | $1,736,000 |

Contingency drawdown this period was $86,000, covering the weather hold and the accelerated transport permits. Forecast cost at completion remains $12,480,000, inside the approved budget.

Distribution: Halvern County DOT, Meridian executive team, Ridgeline Steel (sections 2-3 only).

Fictional sample document created by DocuPipe for demonstration - www.docupipe.ai/tools/word-to-excel